## Sheet1
START DATE: | START DAY: | JOB NUMBER: |  | 202401-034F |  |  | ADDRESS:
9/11/2024 | WEDNESDAY | JOB NAME: |  | ASSOCIA ONCALL |  |  | 354 LARSDOTTER LN, GENEVA, IL
END DATE: | END DAY: | AREA OF DESCRIPTION: |  | KITCHEN AREA UPSTAIRS
9/11/2024 | WEDNESDAY | LOSS CAUSE: |  | FIRE
| EMPLOYEE: |  | START TIME: | END TIME: | LUNCH: | TOTAL HOURS: |  | EMPLOYEE SIGNATURE:
1 | JUAN GALLEGOS |  | 7:00 AM | 5:15 PM | 0:30 | 9.75 |  | JUAN GALLEGOS
2 | JOSE SORIA |  | 7:00 AM | 5:15 PM | 0:30 | 9.75 |  | JOSE SORIA
3 | STHEFANY SPAGNUOLO |  | 9:00 AM | 3:00 PM | 0:30 | 5.5 |  | STHEFANY SPAGNUOLO
4 | WALTER BERMUDEZ |  | 9:00 AM | 3:00 PM | 0:30 | 5.5 |  | WALTER BERMUDEZ
5 | CARLOS PEREZ |  | 9:00 AM | 3:00 PM | 0:30 | 5.5 |  | CARLOS PEREZ
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
16 | [5 empty] | 0
17 | [5 empty] | 0
18 | [5 empty] | 0
19 | [5 empty] | 0
20 | [5 empty] | 0
21 | [5 empty] | 0
22 | [5 empty] | 0
9-11-2024 UPDATE Loaded up all consumables for todays job scope such as, Masonite, 6 mil poly, 4 mil poly, painters plastic, card board boxes, etc. mobilized to job site Arrived on site gained access to unit 348 through garage door and unit 360 lock box is on site code for lock box is (1011) garage door code for unit 348 (9999) met Tristian on site went through job scope for unit 360 with him and Andrew. * Unit 360 we began to set up protect in living area hardwood flooring and kitchen area putting down ram board and Masonite on top. Upper and lower cabinets were covered up with card board boxes and covered up with plastic on top. Unit still has the whole upstairs that needs to protect and first floor still needs to be finished.